## README
Fishway Construction Checklist
Please Read this Page before Using the Fishway Construction Checklist!
This is a checklist for project sponsors and managers on how to proceed with designing and constructing a small fishway at a small dam. This is intended for dams that do
not generate electricity (FERC non-jurisdictional) and rely on voluntary participation by the dam owner and likely the use of grants or outside money. There are also checklists
for eel passes, dam removals, Aquatic Organism Passage, Stream Profiles, and Small screens. If one of these better describes the projects you are interested, find a more
appropriate checklist. No checklist will be perfect or relevant to every potential project. However, this checklist is offered as a helpful guide for inexperience project managers
or project sponsors and it was developed by people who have experience with this kind of project. The checklist may have to be adapted to your particular situation.
The Education Committee of the BioEngineering Section (BES) of the American Fisheries Society (AFS) is providing a series of checklists for implementing fish passage and habitat projects as a service to our community of practice, especially newer practitioners and on the ground project managers. These checklists are provided with the intent of fostering more successful projects with fewer missteps and less backtracking. The following are a few notes to help make use of these checklists:
The checklists are targeted to common, small and moderate scale civil works projects being performed to remedy fish passage problems or for habitat improvement. They are not meant to address large and complex projects, nor will they perfectly serve all cases.
The checklists are to be used as prompts to consider what to enact or provide for a particular project type. The intent is not that each item should be performed, but the practitioner should consider each item to determine if it is required or beneficial to a successful project. It is unlikely that any project will enact ALL the items on a checklist, and conversely these checklists should be considered a starting point, with additional steps that may be necessary for a site or geographic area.
Individual checklists have been assembled for Aquatic Organism Passage, Fishways, Eel Passes, Dam Removals, Stream Profile Control, and Small Screens. Additional check lists may be included over time. Checklists were developed by experts in each type of project, based on the best available guidance rooted in existing science, engineering and training resources.
These checklists are not being endorsed by AFS or BES. There are other project checklists available from other authorities on these topics. Some can be found within training documents found at our other product, the Fish Passage Training Portal, available at the project homepage linked below. If you think the below collection of checklists would benefit from another category of project or have other feedback, please write to: water@terraserve.net
Glossary: |  | A glossary of terms related to fish passage and stream restoration implementation has been compiled from various sources into a single file for ease of reference and can be downloaded from the project home page. | Project Home Page:
https://units.fisheries.org/fishpassagejointcommittee/fishpassagetrainingportal/
Fish Passage Training Portal: |  | A compendium of fish passage-related training resources and links to electronic data developed to provide a centralized and vetted list of resources to new practicitioners or those looking to expand their knowledge.
Principal Checklist Author: Stephen Gephard (CT)

## Fishway Checklist
Building Small Fishways: A Basic Guide for Project Managers -
(non-FERC licensed projects)
□ | Step 1: Identify owner of dam
□ | Step 2: Determine if the owner would support the construction of a fishway (assuming owner will not support dam removal)
□ | Step 3: Consult with State Fisheries agency to confirm value of a fishway (suitable upstream habitat, existing fish runs)
If affirmative responses from steps 2 and 3, proceed. If not, terminate effort.
□ | Step 4: Identify to project sponsor (agency, NGO, Muncipality, etc.) as well as future owner/operator of the fishway
□ | Step 5: Identify/Recruit a good Project Manager
□ | Step 6: Initial information gathering
A- Site visit (never proceed with a project without key project personnel visiting the site) SEE TAB 6A
B- Other information that may affect viability or design SEE TAB 6B
□ | Step 7: Consider funding. (note that grants are sometimes for design OR construction. This checklist assumes you start with design and construction is a second phase.)
A- Often confirm the availability of grants or funding opportunities prior to initiating process SEE TAB 7A
B- applications are developed once you have a credible plan and a estimate of how much design will cost you. Plans could fall into one of the two categories listed below:
1) You have a conceptual plan for the fishway (location, style, layout, etc.)
2) You do not have a conceptual plan and will ask engineers to either provide an Alternatives Analysis (several options) or jump right to their preferred alternative.
C- Consult with the funders, if possible/necessary to ensure best possible application
D- Follow instructions carefully
E- Letters of support are usually required so think ahead of whose support will help the application
Remaining checklist assumes grant award
□ | Step 8: Develop public outreach strategy. Most fishways are not as controversial as dam removals but good public outreach will identify
potential conflicts and address them early as well as maximize public support for the project. Carried on throughout balance of project.
May include public information meetings, websites, etc.
□ | Step 9: Craft any agreement required by grantor to formalize relationship and make funds available for the project.
□ | Step 10: Develop Proposed Scope-of-Work (SOW) that selected engineering firm would be hired to do
□ | Step 11: Create a list of qualified engineers who will be considered for the job. If unsure of such engineers, consult with partners and agencies.
□ | Step 12: Issue an Request for Proposals (RFP) to Engineers on list (or otherwise following procedures for bidding that sponsoring org/agencies require)
A- include a pre-bid mandatory site visit for any engineer to be considered (you don't want to hire a firm that has never seen the site)
B- include proposed SOW. This should include a timeline that the sponsor wishes to follow, e.g. when you hope design will start and when you expect full completion of the tasks.
C- list any relevant restrictions that could affect bids (e.g. cannot access from right bank, no noise after 3 pm, no instream work after Sept. 30, all sediment must be hauled off-site)
D- if the team has identified a particular concept for fishway (site, style, etc.), include it. If engineer is to perform an alternatives analysis and evaluate for the sponsor several options, state such in the RFP
E- provide details on what you expect in each proposal SEE TAB 12D
□ | Step 13: Select engineer
A- based upon any procedure required by sponsoring organization or agency
B- Determine if the lowest bidder is required to be chosen; if not, ensure the chosen engineer is capable of providing the best services, based upon RFP
C- if there is no prescribed procedure in place, a 3-5 personal selection panel is recommended to review all proposals and independently score each before meeting to compare and gain consensus
D- once a prefered candidate is identified, enter into discussions prior to notifying others that they were not chosen.
E- discuss a revised SOW with selected engineer, based upon its proposal and those of other competing firms (the proposals may have identified new issues)
F- Once it is clear that you will be able to hire the selected firm, notify the other candidates of your decision.
G- Once a revised SOW and price is successfully negoitated, sign contract, which among other things specifies how payments will be made.
□ | Step 14: Design the fishway
A list of steps and components to designing a fishway are found in TAB 14.
Each project is different and not all of the items listed in TAB 14 may be needed for your project.
□ | Step 15: | Apply for Permits. SEE TAB 15 FOR A LIST OF COMMONLY-NEED PERMITS
Each State is different. It is important that the sponsor and its engineering firm have done the necessary homework to determine which permits are required for its project
The sponsor should review each permit requirements and understand what information is necessary for required permits. Consult with experienced people or permitting agencies to clarify.
Understand what conditions will likely be part of permits will affect contractors hired to build the fishway. E.g. in some states no instream construction is allowed between October 1 and June 1.
Fill out application forms and submit according to instructions.
Some permits take many months to obtain. If you are confident that permits will be issued, you can proceed with next steps while you await the permits to be issued.
□ | Step 16: If the final plans make clear that temporary construction or permanent easements will be required for adjacent properties, begin negotiations to secure such easements.
□ | Step 17: | Apply for construction funds
Many grants are awarded for design and planning only or construction only. If you have received only a design grant, you now need to apply for a grant to build. This application can be submitted as soon as you have plans
and a cost estimate from the engineer. If permits are not yet secured, you indicate in your grant application which permits have been applied for.
□ | Step 18: Once grant is awarded, craft any agreement required by grantor to formalize relationship and make funds available for the project.
Step 19: Develop Proposed Scope-of-Work (SOW) that selected construction firm would be hired to do. Initially, this can be as simple as "build the fishway shown in these engineered plans".
□ | Step 20: Create a list of qualified contractors who will be considered for the job. If unsure of such contractors consult with partners and agencies.
□ | Step 21: Issue an Request for Proposals (RFP) to Contractors on list (or otherwise following procedures for bidding that sponsoring org/agencies requires)
A- include a pre-bid mandatory site visit for any contractor to be considered (You don't want to hire a contractor who has never seen the site.)
B- include plans and specs
C- provide details on what you expect in each proposal (content, format, page limits, etc.) as well as deadline and means of submission. SEE TAB 21C
□ | Step 22: Select contractor
A- based upon any procedure required by sponsoring organization or agency
B- Determine if the lowest bidder is required to be chosen; if not, ensure the chosen engineer is capable of providing the best services, based upon RFP
C- once a prefered candidate is identified, enter into discussions prior to notifying others that they were not chosen.
D- discuss any revisions proposed by a contractor with your engineer (come contractor proposals may have identified new issues). Sometimes a contractor proposes a better way to control water, etc.
Should be discussed with engineer before agreeing. Accepting revisions could affect agreed-upon price: up or down.
F- Once it is clear that you will be able to hire the selected firm, notify the other candidates of your decision.
G- if a revised SOW and price are successfully negoitated, sign contract, which among other things specifies how payments will be made.
□ | Step 23: Consider construction oversight. The sponsor may be able to provide oversight for small, simple projects. For other projects, Sponsor may hire the design engineer to provide construction oversight. Rates for such oversight
may have been agreed upon when the engineer was hired. Many small projects do not need daily oversight. Pay for only what you need. Identify key times within the construction sequence for oversight. Oversight can be
on an hourly basis (as needed) or a flat fee.
□ | Step 24: Assuming all permits easements are secured, identify a start date. Near start date, hold a kick-off meeting with key members of steering committee, dam owner, engineer, and contractor so everyone is clear on details.
This is a good time to review 'ground rules', e.g. no work on the weekends, don't damage a certain tree, contain engineer at specific milestones, details on site restoration).
□ | Step 25: Proceed with construction activities, in accordance with plans, contract, and permit. Depending upon size of project, hold sporadic or weekly on-site progress meetings to monitor progress and address issues.
□ | Step 26: Once contractor announces completion of project, hold walk-through inspection to determine that the fishway was built according to approved plans and there are no outstanding tasks. It is typical for there to be
a few things on a 'punch list' yet to be done. Sometimes a project is finished too late in the fall or winter to plant grass and site restoration may be completed in the spring.
□ | Step 27: Once all things are completed to the Sponsor's satisfaction, approve the project, close-out the contract, and make final payment.
□ | Step 28: 'As-built' plans should be prepared by the engineer (and be part of the construction oversight agreement). Not all permitters may wish to see such 'as-builts' but regardless, the owner/operator of the fishway will need them.
□ | Step 29: If not already done, finalize agreements, easements, etc. that allow for the ownership and operation of the fishway as well as inspection access to appropriate parties.
□ | Step 30: Finalize a Operaion and Maintenance (O&M) plan for the fishway that spells out who will do what and how in the future to operate and maintain the fishway and ensure effective fish passage. Partners should have previously
reviewed drafts. Such a plan cannot be finalized until the construction is completed so that all features and idiocracies of the fishway are known and can be represented in the Plan.
□ | Step 31: Public outreach.
Sponsor may wish to erect an interpretative sign explaining the fishway, list target species, rules for the site, and acknowledge partners and and funders (which might be a grant requirement)
Sponsor may wish to host a ribbon-cutting event to celebrate and acknowledge partnerships.
Sponsor may wish to add information about fishway to its website, newsletter, etc.
□ | Step 32: Grant Close-out. Each grant award has its own requirements to close-out. Some require a final report with photos, as-builts', financial summary, etc. The Sponsor needs to understand these requirements and submit all
such information to close out the grant and end the project. This pertains to the design grants as well.
Planning & Feasibility
Design
Construction

## Tab 6A- Site visit
Things to address during early site visits:
confirm that target species can reach the base of the target dam
cursory review of dam condition; will substantial repairs to dam be needed to build a fishway?
identify current uses of the dam, impoundment, and water
identify potential complicating factors, e.g. existing buildings, existing fishways, poor construction access, upstream bridges.
identify issues that require further investigation, such as call-before-you-dig, ownership of adjacent properties, legal water rights
identify likely location for the fishway
if not otherwise available, take basic measurements needed to proceed, e.g. height of dam

## Tab 6B- Other information
OTHER VALUABLE INFORMATION TO GATHER
Learn from owner what are conditions and special needs for a project (e.g. don't cut down that tree)
Assess potential community interests/concerns – flooding, recreation, historic, habitat
Identify land ownership boundaries around the dam, future fishway site, and likely construction access route
Determine what easements (either construction or permanent) will be requirement for this project
Identify any listed species in the area that might be a factor in permitting
Identify any historical resources in the area that might be a factor in permitting (anticipating section 106 consultation)
Identify sources of information that will be important, e.g. USGS gage station; watershed plans; recovery plans; previous studies.
Collect and synthesize all available existing data on the dam, the river, and the surrounding landscape. This could include:
a. Existing maps and plans, including:
i. As-builts (plans that show how the original dam was constructed)
ii. Dam dimensions and year built
iii. Dam materials, operations, and maintenance history
b. Past dam inspections and dam safety reports
c. FEMA Flood Insurance Studies
d. Aerial photos
e. Historic maps
f. Fisheries data
g. Planning department reports
h. Utilities mapping, including water lines, power lines, sewer lines, and other infrastructure that could be impacted by heavy machinery in the area
NOTE- some of the above information need not be collected by the sponsor but could be collected by the selected engineer. Whatever the sponsor can collect will reduce cost of a Scope of Work for engineers.
In any case, it is good to know what is available and even if the engineering firm is responsible for collecting and analyzing the information, if the sponsor is able to tell it where to obtain the information, it will
expedite the process.

## TAB 7A- funding opportunities
POTENTIAL FUNDING SOURCES
NOAA Funding Opportunities
U.S. Fish and Wildlife Service – National Fish Passage Program
U.S. Fish and Wildlife Service – Partners for Fish and Wildlife Program
National Fish Habitat Partnership
National Fish and Wildlife Foundation (check for local relevant programs like Long Island Sound Future Fund or Joint Brook Trout Venture)
Natural Resources Conservation Service – Environmental Quality Incentives Program (EQIP)
Natural Resources Conservation Service – Watershed and Flood Prevention Operations Program
U.S. Army Corps of Engineers – Aquatic Ecosystem Restoration
State Funding Sources
Local Funding Sources
Private Funding Sources (e.g. local foundations dedicated to geographic areas or conservation)
Additional Funding References

## TAB 12D- details for the RFP
THINGS TO CONSIDER TELLING BIDDING ENGINEERING FIRMS ABOUT THE PROPOSALS THAT THEY NEED TO SUBMIT
Overview of the firm and its experience in fishway design
List of fishways that the firm has designed, indicating which of the fishways have been built
List of firm's staff who will be assigned to this project and their qualifications
Summary of the firm's technical approach and work plan, demonstrating project understanding
Firm's proposed SOW that lists tasks (e.g. surveying, information gathering, 30% design, meeting attendance). NOTE: It is typical for a firm to provide plans for the sponsor to review at 30%, 60%, and 90% levels of completion. SOW should also include the firm's opinion of probable cost (for construction).
Firm's proposed deliverables that include what would be provided in a final set of plans, e.g. number of sheets including profile and plan views, water handling plan, etc.
Proposed timeline
cost/fee proposal, broken down by task
Other options (price structure for construction oversight)
Set page limit, otherwise some large firms will give you a 100-page submittal
Set submmittal deadline and provide how to submit. (Electronic submittals are best because easier to share with partners.)
In the RFP, tell them how you will evaluate the proposals and when you hope to select a firm.

## TAB 14- common steps in design
COMMON TASKS AND COMPONENTS TO DESIGNING A FISHWAY
Collect existing data
Survey and map the site
Assess hydrology (watershed scale) and hydraulics (local scale)
Assess sediment quantity, quality if significant excavation into the headpond is necessary
Assess condition of the dam and anticipate any remedial actions State dam safety programs might require
Develop conceptual drawings or preliminary design plans (~30% completion) to include the type and location of the fishway style, basic fishway geometry, construction access route, basic construction sequence.
Steering committee meets with engineer to review and approve 30% plans.
Once 30% plans are approved, proceed toward final design (with possible reviews at 60% and 90%)
Once 30% plans are approved, project sponsor or engineer can begin to assess the following:
Whether listed species will be impacted and how to respond to permitters' concerns
Consult with State Historical Preservation Office (SHPO) and maybe Tribal Historical Preservation Offices (THPO) to determine if historical resources need protection
NOTE: SHPO may require an archaeological assessement conducted by an professional archaeologist, who would be hired by the Sponsor. The report, submitted to SHPO by sponsor,
may include recommendations to SHPO that SHPO may require the Sponsor to do, e.g. avoid disturbing a sensitive area, or photodocument a portion of a dam impacted by the project.
Determine which permits (state and federal) will be required.
Once 60% plans are reviewed and approved, determine if the local state agency (lead permitter) offers pre-application meetings. These can be very helpful to identify deficiencies/issues prior to applications
Learn permit lead times. Some state permits make take more than a year to obtain!
Once 90% plans are reviewed and approved, apply for permits (see below). At this point, the engineer should be able to provide cost estimates for construction, which is critical for future fund raising.
Once 90% plans are approved, the plans could be put out to bid (see below) if appropriate. Often, a project is not bid until permits are secure unless the sponsor is very confident of securing permits soon.
Permits may be issued contingent on revisions to the plans. Final 100% plans should be developed to address any outstanding comments/requirements.
Advanced plans typically include:
a. Existing site conditions
b. Staging areas and access
c. Proposed site conditions (overview of fishway lay-out)
d. fishway design (plan view)
e. fishway design (profile, including call out on slopes and projected water levels such as typical, low, and high spring levels from headpond, down fishway, to tailwater)
f. fishway design (several cross-sections, views may vary depending upon the chosen style of fishway)
g. fishway design (detail on entrance, exit, resting pools, etc.). Depending upon size of project, some of these details could be on preceding sheet.
h. If it is a steeppass fishway, usually shop drawings are including along with more details, such as stoplogs, cover gratings, grating lock downs, etc.
d. Water control plan (sometimes modified by the contractor at a later stage but with engineer approval)
e. Delineation of special resource areas (e.g. turtle protection areas, northern longeared bat trees to be protected, etc.)
i. Erosion prevention and sediment control practices
j. site restoration details
Plans are typically accompanied by a Project Specification document (unless it is a very small project in which case specs are included directly on plans):
a. Construction equipment needs
b. Material specifications and quantities
c. Project sequencing
d. Staging area treatment
e. Site access route treatment
g. Other site-specific details such as planting plans, traffic control, infrastructure protection, etc.
As part of the design process, the engineering firm should use its 90% (or 60%) plans to provide an opinion of probable cost for constructing the fishway. Critical for grant applications.
Also, it is likely that the sponsor will need the firm to provide construction oversight during construction. This should be part of the SOW and negotiations. Some firms want a flat rate, some want to bill by the hour.
Sponsors should not hire a firm to do what it can do for free. Some engineering firms will mail out the bids and charge to lick the stamps. Be clear on what you need for construction oversight and negotiate a price
accordingly. Construction oversight is not really part of the design phase but should be part of the firms' proposals (how to bill, at what rate, etc.) because once you choose a firm for design, you're pretty much stuck
with it for construction oversight. If two firms are close in price but the lowest bidder says that it will bill oversight at $500/hour and the next bidder says $150, the lowest bidder may not actually be the lowest bidder.

## TAB 15- Some Typical permits
Permits That You Likely Need to Obtain Include:
State Dam Safety (In some states, this may be the lead agency. Good to start here and learn what other permits would be needed.)
Clean Water Act (CWA), Section 401 Water Quality Certification
Clean Water Act (CWA), Section 404 Permit
Nationwide Permit #27, Aquatic Habitat Restoration, Establishment, and Enhancement Activities
| National Historic Preservation Act, Section 106 (Consultation) |  | Especially if you're using federal funds
You Might Also Need Other State-Specific Permits or Approvals Related to:
Rivers and Harbors Act, Section 10 Permit
Construction Near Wetlands and Waterways
General Construction Activity
Sediment and Stormwater Management and Erosion Control
State Dam Safety
Highway or Transportation Related Issues
Forest Conservation
Historic Preservation

## TAB 21C- Construction bids
THINGS TO CONSIDER TELLING BIDDING CONSTRUCTION COMPANIES ABOUT THE PROPOSALS THAT THEY NEED TO SUBMIT
Overview of the company and its experience in fishway construction
List of fishways that the company has built
Summary of the work plan and proposed construction sequence, providing justification for any deviationis from the engineers' plans
Sometimes a design leaves certain tasks up to the contractor, like water control. If this is the case, the company should outline its plans for water control, etc.
A design usually calls out specific amounts (e.g. yards of soil or rip-rap). If the plan is not specific, ask the companies to set a unit rate they will charge (e.g. $100/yard of rock)
Proposed timeline Your RFP should outline when you want the construction to begin and end. This may be longer than what is needed. But the company should tell you what its workload is and confirm that it can do the job in the time frame you require.
cost/fee proposal, broken down by task
Other options- sometimes a sponsor may be considering an add-on (e.g. pave an existing parking lot) that is not part of the project. If you wait prices for such things, they can be listed outside the total cost.
Generally a page limit is not needed since construction companies are not as verbose as engineers
Set submmittal deadline and provide how to submit. (Electronic submittals are best because easier to share with partners.)
Tell them how you will choose and when you expect to make an decision.