## README
`
Profile Control Scope of Work Checklist
Please Read this Page before Using This Checklist!
Notes Specific to this Checklist:
| 1 | Channel Profile Control is often used as fish passage remedy in itself (e.g regrading a stream below an existing pipeline, road or syphon crossing a stream OR as a componet of another project (e.g. dam removal , road crossing retrofit) to solve a discontiunity in the vertical longitudinal profile of a channel..
| 2 | This Version (Version 1) contains only the basic feasibility checklist with a minimum of references and details.
| 3 | The checklist is to be used as an aid when scoping out the design and construction of a profile control project. Its main utility is to consider the need for, and assign responsiblity for, tasks typical to the development of such a project. Unlike some of the other checklists, it is NOT a comprehensive design guide.
About the Checklists:
The Education Committee of the BioEngineering Section (BES) of the American Fisheries Society (AFS) is providing a series of checklists for implementing fish passage and habitat projects as a service to our community of practice, especially newer practitioners and on the ground project managers. These checklists are provided with the intent of fostering more successful projects with fewer missteps and less backtracking. The following are a few notes to help make use of these checklists:
The checklists are targeted to common, small and moderate scale civil works projects being performed to remedy fish passage problems or for habitat improvement. They are not meant to address large and complex projects, nor will they perfectly serve all cases.
The checklists are to be used as prompts to consider what to enact or provide for a particular project type. The intent is not that each item should be performed, but the practitioner should consider each item to determine if it is required or beneficial to a successful project. It is unlikely that any project will enact ALL the items on a checklist, and conversely these checklists should be considered a starting point, with additional steps that may be necessary for a site or geographic area.
Individual checklists have been assembled for Aquatic Organism Passage, Fishways, Eel Passes, Dam Removals, Stream Profile Control, and Small Screens. Additional check lists may be included over time. Checklists were developed by experts in each type of project, based on the best available guidance rooted in existing science, engineering and training resources.
These checklists are not being endorsed by AFS or BES. There are other project checklists available from other authorities on these topics. Some can be found within training documents found at our other product, the Fish Passage Training Portal, available at the project homepage linked below. If you think the below collection of checklists would benefit from another category of project or have other feedback, please write to: water@terraserve.net
| Glossary: |  | A glossary of terms related to fish passage and stream restoration implementation has been compiled from various sources into a single file for ease of reference and can be downloaded from the project home page. | Project Home Page:
https://units.fisheries.org/fishpassagejointcommittee/fishpassagetrainingportal/
| Fish Passage Training Portal: |  | A compendium of fish passage-related training resources and links to electronic data developed to provide a centralized and vetted list of resources to new practicitioners or those looking to expand their knowledge.

## Profile Control - Scope of Work
Profile Control/Fish Passage Scope of Services Checklist (page 1) adapted from Laura Wildman
for Engineering Consulting Services relating to the Feasibility Study, Design, and/or Construction
Profile Control (e.g. rock wiers, roughened channel, boulder garden) is often a component of an fish passage project (such as a road crossing ,small dam removal or gravity
Phase:
Location:
Project Goals:
Items
Needed |  | Note: These tasks are not in chronological order, but instead have been divided into 12 primary sections.
I. Data Collection & Start Up
|  | A. | Identification/Listing of Project Partners (identification of roles)
|  | B. | Field Assessment - Investigation (site visits)
|  | C. | Data Collection & Review of Existing Material (Mapping, FEMA data, Utilities & U/S Structures, etc.)
(see data collection form) (can put data on GIS database if project merits)
|  | D. | Aerials (orthophotoquad)
|  | E. | Investigation of Infrastructure (i.e. utilities, docks, retaining walls, intakes, etc.)
|  | F. | Historic/Archaeology Study (professional analysis and/or informal investigation of sites past)
|  | G. | Identification of known Rare & Endangered Species within Project Limits (contact authorities)
|  | H. | Project Context (Utilization of a watershed plan; understanding of greater geomprhic context; system issues, etc)
|  | I. | Set Photo points & start Photographing Site
II. Survey
|  | A. | Survey (site & in-channel ) Type: at minimum, site topo near treatement reach, xsections and profile (preferred - bathymetric)
(Property boundaries, limits of U/S impoundments, utilities)
|  | B. | Preparation of Base Maps Scale & Contour Interval: such that active work are fits on one plan sheet, with separate sheet of full impoundment
|  | C. | Pre- Project Longitudinal Vertical Profile Survey
|  | D. | Easement Maps
|  | E. | Wetland Delineation & Vegetation Survey
|  | F. | Delineation of other resource areas (i.e. high water line, banks, regulated areas, etc.)
|  | G. | Property Deed Review
III. Soil Investigation and Analysis
|  | A. | Soil Investigation Plan
|  | B. | Sediment Probes to determine near surface properties
|  | C. | Soil & Bedrock Borings (mechanical) (Borings maybe needed to asses archeological history of site too)
|  | D. | Sediment Sample Collection
|  | E. | Downstream Sediment Sample
|  | F. | Upstream Sediment Sample
|  | G. | Identification of Contamination on Site (do you need a Phase I or II Env Assessment)
|  | H. | Physical Lab Analysis
|  | I. | Chemical Lab Analysis
|  | J. | Suitability Analysis & Summary (based on quality - compare sediment quality results to state standards)
|  | K. | Sediment Transport Analysis
(Potential for sediment transport w/ passage alternative; embankment stability)
|  | L. | Soil Disposal Management Options
|  | M. | Streambank Stability Analysis
IV. Hydrology & Hydraulics
|  | A. | Hydrology (gage data or hydrologic model)
|  | B. | Stream Gauging
|  | C. | Groundwater Monitoring
|  | D. | Hydraulics Modeling
|  | E. | Potential Impacts to Flooding
|  | F. | Preparation of Profiles and Cross Sections
|  | G. | Construction Bypass Hydraulics (dewatering)
|  | H. | Bridge Scour Analysis
|  | I. | Analysis of Upstream (stability) & Downstream (capacity) Structures
|  | J. | Physical Model (only in rare cases)
Profile Control/Fish Passage Scope of Services Checklist (page 2) adapted from Laura Wildman
for Engineering Consulting Services relating to the Feasibility Study, Design, and/or Construction
V. Channel Investigation/Analysis
|  | A. | Selection of a Reference Reach
|  | B. | Geomorphic & Ecological Assessment of Channel
|  | C. | Channel Stability Analysis
|  | D. | Restoration Design of Channel (banks, bed material, stream bank vegetation, habitat, etc.)
|  | E. | Substrate Characterization (i.e. visual, pebble count, measure, etc)
|  | F. | Sediment Trasport Analysis
VI. Fisheries
|  | A. | Consult with Local and Regional Fisheries Resource Managers
|  | B. | Identify and Describe Target Fish Species and lifestage
|  | C. | Assessment of Fisheries (collect passage requirement data for target species)
|  | D. | Final model of each site to ensure that no velocity barriers exist
Determination of Upstream and/or Downstream barriers to fish passage. (i.e. culverts, dams, waterfalls, etc.)
VII. Conceptual/Draft Design
|  | A. | Identify Potential Project Issues & Show Stoppers
|  | B. | Alternatives Analysis (benefits, limitations, impacts U/S & D/S of
various fish passage alternatives)
No Action
Rock Ramp/chute
Roughened Channel
Rock Weirs
Boulder Garden
Combination/Other
Bank protection
Combination of Methods
|  | C. | Design Recommendations (meet with agencies, regulatory authorities & project partners
to discuss alternatives prior to written recommendation)
|  | D. | Environmental Evaluation (of recommended alternative)
|  | E. | Conceptual Design Plans
|  | F. | Preliminary Design Report: including narrative of: 1. Project Description - Background, setting, purpose. existing conditonss
|  | G. | Preliminary Design Plans - based on agency & partnership feedback (design plan, E&S,
construction sequence, utilities, notes, details) Should include:
|  | H. | Preliminary Cost Estimates
|  | I. | Cost/Benefit Analysis of Recommended Design (if required)
|  | J. | Design Report (Describes project context, purpose and approach, Summarizes data & analysis; can submit with permits)
VIII. Permits
|  | A. | Pre Application Meeting with Regulators (identification of required permits & critical issues)
|  | B. | Prepare Permits (Local, State, Federal)
|  | C. | Public Meetings (attendance at meetings)
|  | D. | 8-1/2"x11" plans (for ACOE permits) Other sized plans required: __________________
|  | E. | Revise FEMA mapping (if required)
|  | F. | Post-Filing Support & Revisions
VIII. Final Design
|  | A. | Final Design (includes E&S, construction sequencing plan, site restoration plan, grading plan, details, notes, xsections, profiles, etc.)
|  | B. | Structural & Geotechnical Investigation & Design (if needed)
|  | C. | Planting Plan & Invasive Species Management Plan
|  | D. | Site Access
|  | E. | Final Design Plans
|  | F. | Draft Post-construction evaluation and monitoring plan
|  | G. | Final Sediment & Erosion Controls
|  | H. | Project Manual/Specifications (if going out to bid)
|  | I. | Final Quantities & Cost
Profile Control/Fish Passage Scope of Services Checklist (page 3) adapted from Laura Wildman
IX. Project Management & Coordination
|  | A. | Kick-off Meeting,establishement of lines of communication
|  | B. | General Coordination/Management (includes meetings)
|  | C. | Conference Calls
|  | D. | QA/QC process and documentation
|  | E. | Regular Updates/Reporting to Project Partners
|  | F. | Assistance with Grant Identification and Preparation
|  | G. | Identification of Cost Saving Techniques (scopes broken into tasks, identification of tasks
that can be done externally, identification of scheduling issues that might increase costs, etc.)
X. Public Outreach
|  | A. | Develop a Public Outreach Plan for the project (consensus building approach)
|  | B. | Letter of Intent (sent to affected property owners)
|  | C. | Prepare Visuals (colored set of plans, renderings, photo-renderings, photographs, etc.)
|  | D. | Public Outreach Meetings
|  | E. | Development & Coordination of Stakeholders Group (facilitation)
|  | F. | Develop Press Plan (press releases, press events, etc.)
|  | G. | Web Page
|  | H. | Project Dedication Ceremony
|  | I. | Public Education Opportunities
XI. Construction Administration
|  | A. | Bid Support (encourage "value-engineering")
|  | B. | Inspection Services, QA/QC support
|  | C. | Construction Management (includes meetings, progress reports,
change orders, & approve shop drawings)
|  | D. | Prepare As-Built/Record Drawings
|  | E. | Regular Reporting
XII. Monitoring
|  | A. | Development of Monitoring Plan
|  | B. | Monitoring Meetings (with project partners and interested parties - i.e. academic institutions)
|  | C. | Pre-project Monitoring
|  | D. | Monitoring During Construction
|  | E. | Final Post-Project Monitoring Plan
|  | F. | Post- Project Monitoring
Other Project Consideration When Hiring a Consultant
|  | • | Method of Payment (monthly invoices, etc.)
|  | • | Design/Build Option
|  | • | Breaking Scope into Tasks with Individual Costs (such that certain tasks can be done externally)
|  | • | Type of Contract (hourly rate, lump sum, not-to-exceed, etc)
|  | • | Liability & Insurance (project bonding, upfront agreements, etc.)
|  | • | Termination or Suspension Policy
|  | • | Project Schedule (incentives or penalties)
|  | • | Contract Documents
|  | • | Sub-contractor Coordination & Management
|  | • | Deliverables (what are the deliverables and what format should they be in)
|  | • | Number of Copies Needed
|  | • | Travel Time & Expenses
|  | • | Miscellaneous Project Expenses