## README
Small Screen Scope of Work Checklist
Please Read this Page before Using the Small Screen Scope of Work Checklist!
Notes Specific to this Checklist:
| 1 | This checklist is intended to address planning and execution of small routine fish screen projects as are found at agricultural, municipal, industrial and small hydropower water diversions.
| 2 | This Version (Version 1) contains only the basic scope of work checklist with a minimum of references and details.
| 3 | This checklist is NOT intended to address screening requirements under EPA commonly known as 316b. For more information on these specialty screens, please see: https://www.epa.gov/cooling-water-intakes.
| 4 | The checklist is to be used as an aid when scoping out the design and construction of a small screen project. Its main utility is to consider the need for, and assign responsiblity for, tasks typical to the development of such a project. Unlike some of the other checklists, it is NOT a comprehensive design guide.
About the Checklists:
The Education Committee of the BioEngineering Section (BES) of the American Fisheries Society (AFS) is providing a series of checklists for implementing fish passage and habitat projects as a service to our community of practice, especially newer practitioners and on the ground project managers. These checklists are provided with the intent of fostering more successful projects with fewer missteps and less backtracking. The following are a few notes to help make use of these checklists:
The checklists are targeted to common, small, and moderate-scale civil works projects being performed to remedy fish passage problems or for habitat improvement. They are not meant to address large and complex projects, nor will they perfectly serve all cases.
The checklists are to be used as prompts to consider what to enact or provide for a particular project type. The intent is not that each item should be performed, but the practitioner should consider each item to determine if it is required or beneficial to a successful project. It is unlikely that any project will enact ALL the items on a checklist, and conversely these checklists should be considered a starting point, with additional steps that may be necessary for a site or geographic area.
Individual checklists have been assembled for Aquatic Organism Passage, Fishways, Eel Passes, Dam Removals, Stream Profile Control, and Small Screens. Additional check lists may be included over time. Checklists were developed by experts in each type of project, based on the best available guidance rooted in existing science, engineering and training resources.
These checklists are not being endorsed by AFS or BES. There are other project checklists available from other authorities on these topics. Some can be found within training documents found at our other product, the Fish Passage Training Portal, available at the project homepage linked below. If you think the below collection of checklists would benefit from another category of project or have other feedback, please write to: water@terraserve.net
| Glossary: |  | A glossary of terms related to fish passage and stream restoration implementation has been compiled from various sources into a single file for ease of reference and can be downloaded from the project home page. | Project Home Page:
https://units.fisheries.org/fishpassagejointcommittee/fishpassagetrainingportal/
| Fish Passage Training Portal: |  | A compendium of fish passage-related training resources and links to electronic data developed to provide a centralized and vetted list of resources to new practicitioners or those looking to expand their knowledge.

## Small Screen Scope of Work
Small Fish Screen Scope of Services Checklist (page 1) adapted from Laura Wildman
for Engineering Consulting Services relating to the Feasibility Study, Design, and/or Construction
Project:
Phase:
Location:
Project Goals:
Items
Needed |  | Note: These tasks are not in chronological order, but instead have been divided into 12 primary sections.
I. Data Collection & Start Up
|  | A. | Identification/Listing of Project Partners (identification of roles)
|  | B. | Identify Existing & Past Uses of Diversion
|  | C. | Target species and lifestage to be protected by fish screen
|  | D. | Field Assessment - Investigation (site visits) , include debris assessment
|  | E. | Data Collection & Review of Existing Material (Mapping, FEMA data, Utilities & U/S Structures, etc.)
|  | F. | Aerials (orthophotoquad)
|  | G. | Ownership & Flowage Rights, Bypass requirements
|  | H. | Investigation of Infrastructure (i.e. utilities, docks, retaining walls, intakes, etc.)
|  | I. | Historic/Archaeology Study (professional analysis and/or informal investigation of site's past)
|  | J. | Identification of known Rare & Endangered Species within Project Limits (contact authorities)
|  | K. | Project Context (Utilization of a watershed plan; understanding of greater system issues, timing with other diversions, etc)
|  | L. | Set Photo points & start Photographing Site
______________________________________ |  | M. | Set temporary stage gage (unless gage record available)
II. Survey
|  | A. | Survey (site & in-channel ) Type: at minimum, site topo near diversion, xsections and profile, soundings near intake
(Property boundaries, utilities)
|  | B. | Preparation of Base Maps Scale & Contour Interval: such that active work are fits on one plan sheet, with separate sheet of bypass channel if off stream channel
|  | C. | Easement Maps
|  | D. | Wetland Delineation & Vegetation Survey
|  | E. | Delineation of other resource areas (i.e. high water line, banks, regulated areas, etc.)
|  | F. | Water right and use review
III. Soil Investigation and Analysis (only if adding civil works, including sheetpile, usually not applicable to bolt-on screens)
|  | A. | Soil Investigation Plan
|  | B. | Sediment Probes to determine depth (and quantity)
|  | C. | Soil & Bedrock Borings (mechanical)
|  | D. | Sediment Transport Analysis (some sites)
(Potential for sediment transport w/ passage alternative; flood or seasonal deposition, embankment stability)
|  | E. | Soil Disposal Management Options (some sites)
|  | F. | Streambank Stability Analysis (some sites)
IV. Hydrology & Hydraulics
|  | A. | Hydrology (gage data or hydrologic model) or construction from regional curves
|  | B. | Stream flow vs. depth rating curve at diversion intake
|  | C. | Hydraulics Modeling, target and anticipated approach velocities and sweeping velocities,
|  | D. | Records of diversion flows and stream flows, including maximums and minimums, during diversion season
|  | E. | Preparation of Profiles and Cross Sections base map
|  | F. | Intake Channel and Bypass Hydraulics , predation opportunity reduction
|  | G. | Water Intake Assessment & Redesign
|  | H. | Physical Model (only in rare cases for small screens)
Small Fish Screen Scope of Services Checklist (page 2) adapted from Laura Wildman
for Engineering Consulting Services relating to the Feasibility Study, Design, and/or Construction
V. Channel Investigation/Analysis
|  | A. | Geomorphic & Ecological Assessment of Channel
|  | B. | Channel Stability Analysis
|  | C. | Analysis of changing sediment deposition patterns due to screen and screen protection
|  | D. | Substrate Characterization (i.e. visual, pebble count, measure, etc)
VI. Fisheries
|  | A. | Consult with Local and Regional Fisheries Resource Managers
|  | B. | Identify and Describe Target Fish Species and lfestage presence vs diversion season
|  | C. | Assessment of Fisheries (collect passage requirement data for target species)
VII. Conceptual/Draft Design
|  | A. | Identify Potential Project Issues & Show Stoppers
|  | B. | Alternatives Analysis (benefits, limitations, impacts U/S & D/S of
various fish passage alternatives)
No Action
Repair, replace or relocate diversion (including consolidation).
On-channel screening
off-channel screening and bypass
off-shelf or custom fish screen
permanent, retractable or manually placed mounting
gravity or pumped diversion
screen cleaning - externally powered, paddlewheel, manual; continual or intermittent
debris and sediment deposition handling, traskrack (manual or mechanically cleaned)
C. Design alternatives should include:
_ Compliance with applicable approach velocity and sweeping velocity criteria
_ Water depth and approach velocity calculations in front of the fish screen throughout range of diversion flows
_Evidence that flow uniformity criterion will be met
_Assessment of sediment transport/scour conditions at fish screen for on channel installations
_For larger,custom screens: sweeping velocity calculations at several locations along the length of the screen throughout range of diversion and bypass flows
_Cleaning mechanisms and operation:
_Description of fish screen cleaning mechanism, including proposed frequency of cleaning, access for inspections and cleaning
_ For paddle wheel driven cleaning systems, fish screen area calculations showing passive screening criteria are met when paddle wheel driven wipers no longer operate
If screen includes a bypass (off-channel diversion) also include:
_ Velocity calculations between end of screen and bypass entrance
_ Flow depth calculations within bypass conduit and in stream at bypass outlet at minimum bypass flow
_ Estimated bypass flow needed to meet fish screen criteria
_Velocity calculations in stream at bypass outlet
_Drop height and impact velocity calculation at bypass outlet, if applicable
_ vector (magnitude and orientation) of bypass velocities and receving waters (stream) over range of operation
|  | D. | Design Recommendations (meet with agencies, regulatory authorities & project partners
to discuss alternatives prior to written recommendation)
|  | E. | Environmental Evaluation (of recommended alternative)
|  | F. | Conceptual Design Plans
|  | G. | Preliminary Design Plans - based on agency & partnership feedback (design plan, E&S,
construction sequence, utilities, notes, details)
|  | H. | Preliminary Cost Estimates
|  | I. | Cost/Benefit Analysis of Recommended Design (if required)
|  | J. | Design Report (Describes project and design approach, Summarizes data & analysis; can submit with permits)
VIII. Permits
|  | A. | Pre Application Meeting with Regulators (identification of required permits & critical issues)
|  | B. | Prepare Permits (Local, State, Federal)
|  | C. | 8-1/2"x11" plans (for ACOE permits) Other sized plans required:
|  | D. | Post-Filing Support & Revisions
Small Fish Screen Scope of Services Checklist (page 3) adapted from Laura Wildman
for Engineering Consulting Services relating to the Feasibility Study, Design, and/or Construction
VIII. Final Design
|  | A. | Final Design Report (includes Overall project description and goals, E&S, construction sequencing plan, site restoration plan, grading plan, details, notes, xsections, profiles, etc.)
|  | B. | Structural & Geotechnical Investigation & Design (if needed)
|  | C. | Site Access
|  | D. | Final Design Plans , should include
-Description of fish screen openings, including porosity and dimensions of round, square, or slotted openings
- Specific information describing the type of corrosion-resistant screening material, bypass control/pipe and other materials that will directly affect fish
-Operation and maintenance plan which includes preventive and corrective maintenance procedures, inspection and reporting requirements, acess for O&M, draft maintenance logs, inspecition sheets etc
- Post construction evaluation and monitoring plan
|  | E. | Final Sediment & Erosion Controls, Fish exclusion
|  | F. | Dewatering and fish exckusion plans
|  | G. | Project Manual/Specifications (if going out to bid)
|  | H. | Final Quantities & Cost
IX. Project Management & Coordination
|  | A. | Kick-off Meeting, establishement of lines of communication
|  | B. | General Coordination/Management (includes meetings)
|  | C. | QA/QC process and documentation
|  | D. | Conference Calls
|  | E. | Regular Updates/Reporting to Project Partners
|  | F. | Assistance with Grant Identification and Preparation
|  | G. | Identification of Cost Saving Techniques (scopes broken into tasks, identification of tasks
that can be done externally, identification of scheduling issues that might increase costs, etc.)
X. Public Outreach (if diversion or construction involves greater public)
|  | A. | Develop a Public Outreach Plan for the project
|  | B. | Prepare Visuals (colored set of plans, renderings, photo-renderings, photographs, etc.)
|  | C. | Development & Coordination of Stakeholders Group (facilitation)
|  | D. | Develop Press Plan (press releases, press events, etc.)
|  | E. | Web Page
|  | F. | Project Dedication Ceremony
|  | G. | Public Education Opportunities
XI. Construction Administration
|  | A. | Bid Support (encourage "value-engineering")
|  | B. | Inspection Services
|  | C. | Construction Management (includes meetings, progress reports,
change orders, & approve shop drawings)
|  | D. | Prepare As-Built/Record Drawings
|  | E. | Regular Reporting
XII. Monitoring
|  | A. | Development of Monitoring Plan
|  | B. | Monitoring Meetings (with project partners and interested parties - i.e. academic institutions)
|  | C. | Pre-project Monitoring
|  | D. | Monitoring During Construction (including QC)
|  | E. | Final O&M plan and inspection sheets
|  | F. | Post Project Monitoring
Small Fish Screen Scope of Services Checklist (page 4) adapted from Laura Wildman
for Engineering Consulting Services relating to the Feasibility Study, Design, and/or Construction
Other Project Consideration When Hiring a Consultant
|  | • | Method of Payment (monthly invoices, etc.)
|  | • | Design/Build Option
|  | • | Breaking Scope into Tasks with Individual Costs (such that certain tasks can be done externally)
|  | • | Type of Contract (hourly rate, lump sum, not-to-exceed, etc)
|  | • | Liability & Insurance (project bonding, upfront agreements, etc.)
|  | • | Termination or Suspension Policy
|  | • | Project Schedule (incentives or penalties)
|  | • | Contract Documents
|  | • | Sub-contractor Coordination & Management
|  | • | Deliverables (what are the deliverables and what format should they be in)
|  | • | Number of Copies of Deliverable Documents Needed
|  | • | Travel Time & Expenses
|  | • | Miscellaneous Project Expenses
2