## README
AOP/Stream Simulation Checklist
Please Read this Page before Using This Checklist!
The Education Committee of the BioEngineering Section (BES) of the American Fisheries Society (AFS) is providing a series of checklists for implementing fish passage and habitat projects as a service to our community of practice, especially newer practitioners and on the ground project managers. These checklists are provided with the intent of fostering more successful projects with fewer missteps and less backtracking. The following are a few notes to help make use of these checklists:
The checklists are targeted to common, small and moderate scale civil works projects being performed to remedy fish passage problems or for habitat improvement. They are not meant to address large and complex projects, nor will they perfectly serve all cases.
The checklists are to be used as prompts to consider what to enact or provide for a particular project type. The intent is not that each item should be performed, but the practitioner should consider each item to determine if it is required or beneficial to a successful project. It is unlikely that any project will enact ALL the items on a checklist, and conversely these checklists should be considered a starting point, with additional steps that may be necessary for a site or geographic area.
Individual checklists have been assembled for Aquatic Organism Passage, Fishways, Eel Passes, Dam Removals, Stream Profile Control, and Small Screens. Additional check lists may be included over time. Checklists were developed by experts in each type of project, based on the best available guidance rooted in existing science, engineering and training resources.
These checklists are not being endorsed by AFS or BES. There are other project checklists available from other authorities on these topics. Some can be found within training documents found at our other product, the Fish Passage Training Portal, available at the project homepage linked below. If you think the below collection of checklists would benefit from another category of project or have other feedback, please write to: water@terraserve.net
Glossary: | A glossary of terms related to fish passage and stream restoration implementation has been compiled from various sources into a single file for ease of reference and can be downloaded from the project home page. | Project Home Page:
https://fishpassagejointcommittee.fisheries.org/resources/fishpassagetrainingportal/
Fish Passage Training Portal: | A compendium of fish passage-related training resources and links to electronic data developed to provide a centralized and vetted list of resources to new practicitioners or those looking to expand their knowledge.
THIS SPREADSHEET CHECKLIST WAS DEVELOPED TO SUPPORT STREAM SIMULATION PLANNING, SITE ASSESSMENT, DESIGN, AND CONSTRUCTION. THIS LIST WAS DEVELOPED BY THE NATIONAL STREAM AND AQUATIC ECOLOGY CENTER NATIONAL AOP TEAM (BOB GUBERNICK, DAN CENDERELLI, MARK WEINHOLD, AND ERICA BORUM) WORK COME FROM THE US FOREST SERVICE STREAM SIMULATION METHODOLOGY PUBLICATIONS
Cenderelli, D., Clarkin, K., Gubernick, R., Weinhold, M. Stream Simulation for Aquatic Organism Passage at Road-Stream Crossings. Transportation Research Record. Journal of the Transportation Research Board, 2011
https://www.fs.usda.gov/eng/pubs/pdf/StreamSimulation/hi_res/%20FullDoc.pdf
Stream simulation: An ecological approach to designing road-stream crossings. Stream simulation working group. San Dimas Technology Development Center USDA Forest Service. May 2008
Gubernick. R, Bates. K, Designing culverts for Aquatic Organism Passage: Stream Simulation Culvert Design. International Conference of Ecology and Transportations Proceedings, Lake Placid, NY. 2003
Gubernick. R, Clarkin. K, and Furniss. M, Site Assessment and Geomorphic Considerations in Stream Simulation Culvert Design. International Conference of Ecology and Transportations Proceedings, Lake Placid, NY. 2003
Connor, A. Clarkin, K., Furniss, M., Gubernick, R., Moynahan, K., Wilson-Musser, S., National Inventory and Assessment Procedure for Identifying Barriers to Aquatic Organism Passage at Road-Stream Crossings, May 2003.
THE INTENT OF THIS CHECKLIST IS TO ASSIST PROJECT MANAGERS AND DESIGNERS THROUGH THE STREAM SIMULATION DESIGN PROCESS. THIS IS A LIST OF THE MAJOR STEPS AND DATA REQUIREMENTS. FOR MORE SPECIFICITY PLEASE READ THE ASSOCIATED PUBLICATIONS.
QUESTIONS - PLEASE CONTACT ROBERT.GUBERNICK @USDA.GOV AT THE NATIONAL STREAM AND AQUATIC ECOLOGY CENTER

## TAB 1 STRM-SIM DESIGN CHECKLIST
PLANNING |  | STEP | PLANNING
| □ | 1 | SELECT WATERSHED
| □ | 1a | Determine crossing locations in watershed
| □ | 2 | CONDUCT FISH PASSAGE ASSESSMENTS
| □ | 3 | SURVEY AND COLLECT STRUCTURE DATA
| □ | 4 | ANALYZE AND DETERMINE
| □ | 4a | Determine method of analysis
| □ | 4b | Type of Barrier (full, partial, temporal, species specific)
| □ | 4c | Fish and other aquatic organisms affected by barrier
| □ | 4c1 | Endangered Species
| □ | 4c2 | Timing, swimming ability
| □ | 4d | Barriers upstream and downstream from the structure
| □ | 4e | Terrestial species affected
| □ | 4f | Structure priority for replacement
|  | 5 | UPSTREAM HABITAT ASSESSMENTS
| □ | 5a | Determine habitat quantity and quality upstream of the site(s)
| □ | 5b | Determine water quality concerns
|  | 6 | RESOURCE VALUES
| □ | 6a | Aquatic and riprian dependent fish and wildlife populations
| □ | 6b | Aquatic habitat requiring protection
| □ | 6b1 | Quality and extent upstream of structure
| □ | 6b2 | Critical habitat downstream
| □ | 6c | Floodplain / wetland habtat
| □ | 6d | Water supply
| □ | 6e | Recreation
| □ | 7 | NEPA
| □ | 7a | Conduct NEPA
| □ | 7b | Select prefered alternative(s)
| □ | 8 | PROJECT OBJECTIVES
| □ | 8a | Develop road management Road
| □ | 8a1 | Traffic level; interuptibility; safety
| □ | 8a2 | Maintenance
| □ | 8a3 | Diversion Potential
| □ | 8b | Stream simulation channel
| □ | 8b1 | Desired design features
| □ | 8b2 | Structure design flows
DECISION |  |  | Select AOP crossing(s) to design
SITE ASSESSMENT |  | STEP | SITE ASSESSMENT (SEE TAB 2)
Large Scale (watershed around the site) Assessment
| □ | 9 | WATERSHED RISK FACTORS
| □ | 9a | Are there geologic or geomorphic hazards (landslides, avalanches, debris torrents, etc. )?
| □ | 9b | What is the Flooding history and other significant geomorphic events.?
| □ | 9c | What is the land management history and projected future change: expected changes in sediment and/or flow regimes?
| □ | 9d | Is channel stability of off-site reaches (location/type/potential to affect site) further upstream and downstream of the project area?
Reach Scale (conditions upstream, downstream and at site) Assessment
| □ | 10 | ROAD DATA AND ENGINEERING CONSTRAINTS
| □ | 10a | Is the road needed? Long-term commitment and plans for road.
| □ | 10b | What are the road managment objectives and level
| □ | 10c | What is the surface composition (paved (asphalt, concrete, gravel?)
| □ | 10d | What is the ADT?
| □ | 11 | LOCATION, HISTORY, ROAD ISSUES
| □ | 11a | What is the road and crossing maintenance history: chronic maintence problems?
| □ | 11b | Are there any Vertical and horizontal constraints on road grade, elevation, and location?
| □ | 11c | Is there diversion potential at the site?
| □ | 11d | Are there any public safety issues (poor site distance,accident history and frequency?
| □ | 11e | Determine Right of Way and ownership along the project area
| □ | 11f | Are there and what is the location for associated infrastructure (Utilities, Pipelines, buildings, etc.)
| □ | 11g | Describe fillslopes:height, stability, encroachment issues.
| □ | 11h | Can you provide construction closure? Are there detour and bypass options?
| □ | 12 | EXISTING STRUCTURE
|  | 12a | Perform a construction survey on crossing
| □ | 12b | What are the structure dimensions, slope, fill, perch, appurtances, etc
| □ | 12c | What material is the structure (steel, concrete, galv. steel, etc.) What is its structural condition?
| □ | 12d | Structure and hydraulic geometry
| □ | 12d1 | What is the structure skew to stream and road?
| □ | 12d2 | Floodplain and bankfull width constrictions
| □ | 13 | PROJECT REACH
Annotated site sketch (measure and develop)
| □ | 13a | What are the Geomorphic features:(channel and floodplain to valley wall)
| □ | 13b | Road features (width, speed, turnouts, etc.?)
| □ | 13c | Vegetation characteristics and trees (whats there and do any of the trees need to be retained)?
| □ | 13d | Land ownership
| □ | 13e | What utilities are there and where are they located and at what depth if below ground?
| □ | 13f | Potential channel lateral adjustment to change inlet geometry (structure to stream alignment)?
| □ | 13g | Locate potential construction access
| □ | 13h | Locate photo points
| □ | 13i | Identify cross section key feature locations (Bankfull width depth, bedrock, thalweg, OHW, etc)
| □ | 13j | Identify grade controls and provide stability rating
| □ | 14 | CHANNEL MORPHOLOGY
| □ | 14a | Describe channel type
| □ | 14b | Survey channel geometry and a construction survey (Min. length 100 ft upand downstream. Note depending on regrade length it may be longer)
| □ | 14b1 | Stream to structure alignment (horizontal and vertical)
| □ | 14c | Long Profile survey (survey all breaks in grade along thalweg 30 bankfull width upstream and downstream of existing structures)
| □ | 14c1 | Channel unit location (pool tail, riffle, runs, pools, pool head, etc)
| □ | 14c2 | Grade controls
| □ | 14c3 | Key features (roughness elements, large wood, steps, boulder clusters, bedrock, etc.)
| □ | 14c4 | Residual pool depths/scour potential
| □ | 14d | Cross section survey (at elevation breaks and features)
| □ | 14d1 | Bankfull width; variability in width
| □ | 14d2 | Bank Height
| □ | 14d3 | Channel roughness
| □ | 14d4 | Flood-prone zone width; floodplain conveyance
| □ | 14d5 | Flood-plain roughness
| □ | 14d6 | locate and survey cross sections for hydraulic model
| □ | 14e | Bed material classification
| □ | 14e1 | Pebble count or other method to estimate gradation (surface material)
| □ | 14e2 | Size and dimensions of grade controls (steps, ribs, etc.)
| □ | 14e3 | Determine size and dimensions of key Pieces / features and their mobility (25 largest stable pieces)
| □ | 14e4 | Visually classify sediment below the armor layer (size range and percent by volume)
| □ | 14e5 | Determine spatial locations, dimensions, protrusions, composition, type for instream roughness elements
| □ | 14f | Groundwater elevation
| □ | 15 | CHANNEL STABILITY
| □ | 15a | Channel Response to existing structure
| □ | 15a1 | Does the existing structure overtop or pass a Q100 flow?
| □ | 15b | Vertical adjustment potential
| □ | 15b1 | Is the streambed mobile? At what discharge?
| □ | 15b2 | What is the range of scour depth (residual pool depth)?
| □ | 15c | Lateral adjustment potential
| □ | 15c1 | What is the bank composition
| □ | 15c2 | Is the bank stable? can it be lowered? If lowered does it require stabilization?
| □ | 15d | Floodplain conveyance
| □ | 15d1 | Does the floodplain convey flow or is it storage?
| □ | 15d2 | Are there historic side channels or floodswales? What are their dimensions?
| □ | 15e | Woody debris
| □ | 15e1 | Is large wood and woody debris available for transport downstream in the channel or on the banks?
| □ | 15e2 | What is the logical size of trees or debris that can move downstream? Is tree length longer than bankfull width?
| □ | 15f | Are there Ice scars or evidence of ice dam building?
| □ | 16 | RISK ASSESSMENT
| □ | 16a | Site history (flood history, past/future land use, geologic/hydrologic setting, etc.)
| □ | 16b | Potential for change in sediment loading/flow regime (large available sediment sources? (alluvial fan, slope failures adjacent to stream, landslides or debris flows?)
| □ | 16c | Are there special geologic conditions at the site? (sand bedded channel channel, cohesive bed, shallow armor over highly erodable material (glacial origin), etc.)
| □ | 16e | Is the channel stable?
| □ | 16f | What is the vertical adjustment potential? (Upper and Lower)
| □ | 16g | Does the channel have Headcut Potential?
| □ | 16h | Is there lateral adjustment potential?
| □ | 16h1 | What is the radius of curvature of the upstream bend divided by Bankfull width?
| □ | 16h2 | What is the vegetation types along the banks? rooting depth of the vegetation?
| □ | 16i | Floodplain conveyance/connectivity
| □ | 17 | REFERENCE REACH
| □ | 17a | Longitudinal Profile (SEE TAB 2)
| □ | 17a1 | Determine gradient
| □ | 17a2 | Determine grade controls and channel unit dimensions (Key features: types, spacing, height, slope, location, protrusions, composition.)?
| □ | 17a3 | How rough is the channel (estimate mannings in channel and floodplain)?
| □ | 17b | Cross section (detailed measurements and characterization)
| □ | 17b1 | Channel form/configuration/geometry
| □ | 17b2 | Bankfull width & depth
| □ | 17b3 | Bedwidth (width and configuration)
| □ | 17b4 | Entrenchment
| □ | 17b5 | Channel Margins and banklines
| □ | 17c | Bed material
| □ | 17c1 | Bed material: gradation, armoring, angularity
| □ | 17c2 | Key features: particle sizes, packing/consolidation
| □ | 17c3 | Bed mobility
PRELIMINARY DESIGN |  | STEP | PRELIMINARY DESIGN (SEE TAB 3)
| □ | 18 | CIVIL DESIGN LAYOUT
| □ | 18a | Determine structure horizontal alignment
| □ | 18b | Select design profile beginning and end points (stable grade controls)
| □ | 18c | Develop channel and structure gradients
| □ | 18d | Determine potential reference segments from long profile analysis and design profile gradient)
DECISION |  |  | Determine if stream simulation can be used based on engineering constraints ( vertical alignment, utilities, ROW, etc, and geomorphic risks)
| □ | 18e | Determine beform and channel unit spacing
FINAL DESIGN |  | STEP | FINAL DESIGN (SEE TAB 3)
| □ | 19 | STRUCTURE DESIGN
| □ | 19a | Select a structure
| □ | 19b | Analyzing the mobility of the stream simulation design channel bed,
| □ | 19c | Analyzing the stability of key pieces and bedforms in the design channel bed for the design flood
| □ | 19d | Evaluating the hydraulic capacity of the selected structure for the design flood,
DECISION |  |  | Determine if selected structure meets design criteria, if not select another structure
| □ | 19e | Developing final bed material specifications for the stream simulation design channel,
| □ | 19f | Develop bed design configuration with instream structures
| □ | 19g | Developing erosion control and dewatering plans, traffic control
| □ | 19h | Preparing the documents necessary for soliciting construction bids

## TAB 2 LONG PROFILE ASSESSMENT
STREAM SIMULATION LONGITUDINAL PROFILE ASSESSMENT PROCESS
LONG PROFILE ASSESSMENT |  | STEP | LONGITUDINAL PROFILE ASSESSMENT PROCESS
| □ | 1 | Identify pools and grade controls.
| □ | 2 | Determine the types of grade controls along the longitudinal profile.
| □ | 3 | Assess the relative stability of each grade control.
| □ | 4 | Determine the geomorphic controls of the pools (Note: compare the longitudinal profile with the planform map)?
| □ | 5 | Delineate slope segments.
| □ | 6 | Calculate the elevation change, length, and gradient of each slope segment. Determine the percent difference between adjacent segments.
| □ | 7 | Determine the maximum scour depth (residual pool depth) for each slope segment and culvert plunge pool. How does culvert pool scour depth compare to other pool depths along profile?
| □ | 8 | Determine the number of and distance between grade controls for each slope segment.
| □ | 9 | Identify and delineate the extent of sediment aggradation (thickness and length) upstream from culvert inlet.
| □ | 10 | Identify the shape of the longitudinal profile.
| □ | 11 | Delineate the upper vertical adjustment potential line along the longitudinal profile. Indicate the geomorphic evidence used to delineate the upper vertical adjustment potential line.
| □ | 12 | Delineate the lower vertical adjustment potential line along the longitudinal he geomorphic evidence used to delineate the lower vertical adjustment potential line.

## TAB 3 STREAM SIM DESIGN PROCESS
STREAM SIMULATION DESIGN PROCESS
PRELIMINARY DESIGN |  | STEP | STREAM SIMULATION PRELIMINARY DESIGN PROCESS
| □ | 1 | Identify one downstream and two upstream design elevation control points (grade controls) to connect the channel through the road-stream crossing.
| □ | 2 | Delineate design channel profile(s) between these points.
| □ | 2A | Calculate the design gradients.
| □ | 2B | Calculate the percent difference in gradients between the design profiles and the channel slope segments.
| □ | 2C | Select your preliminary design profile.
| □ | 3 | Select a preliminary reference reach.
| □ | 4 | Estimate the upper and lower vertical adjustment potential lines through the crossing, initially as parallel to design slope segment. Consider adjustments for site conditions (bends, bedrock, etc.).
| □ | 5 | 5.Use the reference reach as a template to design a new streambed through the design reach.
| □ | 5A | a) From the reference reach, identify the type and dimension of bedforms to construct in the design
| □ | 5B | b) Identify the location of any controls on pools due to stream or structure geometry, bedrock, or other pool forming mechanisms.
| □ | 5C | From the findings in part B) above, layout the number and spacing of bedforms to be constructed in the design channel.
| □ | 6 | Delineate the depth of sediment to fill plunge pool.
| □ | 7 | Explore another design profile option (return to step 2)?
FINAL DESIGN |  | STEP | STREAM SIMULATION FINAL DESIGN PROCESS
| □ | 8 | Select design profile for final design
| □ | 9 | Select a structure type and size (must be below lower VAP and fit around design cross section with banks or margins)
| □ | 10 | Analyzing the mobility of the stream simulation design channel bed, adjust mix as necessary
| □ | 11 | Analyzing the stability of key pieces and bedforms in the design channel bed for the design flood
| □ | 12 | Evaluating the hydraulic capacity of the selected structure for the design flood (Headwater to Depth ratio (HW:D) <0.8
Evaluate design if criteria isnt meet try a different structure shape/size/ gradient
| □ | 14 | Developing final bed material specifications for the stream simulation design channel,
| □ | 15 | Develop bed design configuration with instream structures
| □ | 16 | Develop construction plans
| □ | 17 | Develop schedule of items and cost estimate
| □ | 18 | Develop scope of work and project specifications

## TAB 4 CONSTRUCTION INSPECTION
CONSTRUCTION INSPECTION CHECKLIST
Performed | Number | Item to inspect | Timing | What to check
□ | 1 | Existing ground elevations and evidence of change from site conditions | Before construction | Check existing ground elevations for errors or substantial changes due to floods or changes in site conditions
□ | 2 | Traffic Control | Before construction | Check that the traffic control plan is in accordance with the Manual of Uniform Traffic Control Devices (MUTCD)
□ | 2A |  |  | Check proper placement of devices in accordance with the Contractor approved traffic control plan
□ | 3 | Dewatering | During Construction | Has the dewatering plan been approved?
□ | 3A |  |  | Check dewatering plans and calc’s. Is the plan sufficient for the anticipated dewatering flows?
□ | 3B |  |  | Check dewatering layout on the ground. Is there enough room to work once the dewatering facility is in place?
□ | 3C |  |  | Check coffer dam height, pump and bypass channel capacity
□ | 3D |  |  | Check outflow, is the outflow causing erosion
□ | 3E |  |  | Have the organism been removed and relocated
□ | 3F |  |  | Is turbidity being prevented?
□ | 3G |  |  | Are they checking and replacing sediment bags?
□ | 3H |  |  | Has the contractor moved the outflow for the sump to prevent overland flow from saturated conditions natural infiltration outflow terminus
□ | 4 | Pollution control | Before and during construction | Is there a pollution control plan and has it been approved?
□ | 4A |  |  | Is there a spill kit on site? Does it have the required items in it?
□ | 4B |  |  | Has the downstream oil boom been placed?
□ | 4C |  |  | Is the contractor refueling away from the stream
□ | 4D |  |  | Is oil or fuel stored on site? If so is it within the contract, state, or federal requirements?
□ | 5 | Soil erosion control | Before and during construction | Has the soil erosion control plan been approved?
□ | 5A |  |  | 2. Has soil erosion materials been deployed?
□ | 5B |  |  | 3. Is it functioning properly when it rains?
□ | 6 | Excavation | During construction | Check subgrade elevations, width of trench, and materials before backfilling
□ | 6A |  |  | Check OSHA excavation safety requirements are enforced.
□ | 7 | Foundation and structural embankment | During construction | Does the structural backfill materials meet contract gradation spec?
□ | 7A |  |  | Is compaction occurring according to the contract spec (layer thickness and compaction effort)?
□ | 7B |  |  | Is the finish grade elevation for foundations been verified before placing the structure?
□ | 7C |  |  | Is structural backfill being brought up simultaneously on each side of the structure
□ | 8 | Material | Before and during construction | Have you received material certifications that materials meet contract requirements?
□ | 8A |  |  | Are the materials new, not damaged, the right material type, the right size, shape, and dimensions?
□ | 8B |  |  | Are all the required parts at the site
□ | 9 | Bed preparation | During construction | Is the bed uniform and elevation to grade?
□ | 10 | Structure fabrication | During construction | Are the fabrication plans on site and are they being adhered too.
□ | 10A |  |  | Are concrete forms and rebar as designed
□ | 10B |  |  | Are bolts tightened to required torque
□ | 10C |  |  | Is there gaskets for culverts, are the bands set properly and tightened?
□ | 10D |  |  | Are there voids at band locations where water can escape for pipe arches
□ | 10E |  |  | has the work had proper testing been done? Slump?, break strength?
□ | 10F |  |  | Is the structure aligned vertically and horizontally as shown on the plans?
□ | 10G |  |  | Is there sufficient fill cover over the structure before equipment crosses?
□ | 11 | Road embankment | During construction | does the aggregate meet contract gradation spec (size, durability, etc).
□ | 11A |  |  | Is compaction occurring according to the contract spec (layer thickness and compaction effort)?
□ | 11B |  |  | Are the roadway, shoulders, crown, pavement dimensions, slopes and elevations as designed (vertically and horizontally)?
□ | 12 | Channel bed, roughness, and bank construction | During construction | Do the materials meet the contract gradations, size, length, etc.?
□ | 12A |  |  | Are the channel bed, roughness, and bank elements to proper elevation, spatial distribution, orientation/alignment, thickness, size, etc. and within contract tolerance?
□ | 12B |  |  | Are the banks and grade controls embedded to the lower VAP?
□ | 12C |  |  | Is the bed sealed and has it been properly compacted depending on material size?
□ | 13 | Rewatering | During removal | Ensure water added slowly (no dam break floods.
□ | 13A |  |  | Have the dewatering facilities (coffer dams, pumps, culverts, pumps, etc) been removed and restored?
□ | 14 | Clean up | After construction | Have all unused materials and equipment been removed from the site
□ | 14A |  |  | Has the disturbed areas been regraded back to the original topography and top soil replaced?
□ | 14B |  |  | Does the seed mix and plants meet specification?
□ | 14C |  |  | Has the area been seeded and replanted?
□ | 14D |  |  | Have all designated soil erosion and pollution control devices been removed?