Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts* | • Potential for presence of historic artifacts*
Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly coarse-grained material (less than 10% fines – sand, silt, clay) this technique can be used to determine depth-to-bedrock, and therefore, assist with determining the amount of stored sediment | • Seismic refraction study*– for dams that store mostly 