## READ ME
`
Small Fish Screen Feasibility Checklist
Please Read this Page before Using This Checklist!
Notes Specific to this Checklist:
| 1 | This checklist is intended to address planning and execution of small routine fish screen projects as are found at agricultural, municipal, industrial and small hydropower water diversions.
| 2 | This Version (Version 1) contains only the basic feasibility checklist with a minimum of references and details.
| 3 | This checklist is NOT intended to address screening requirements under EPA commonly known as 316b. For more information on these specialty screens, please see: https://www.epa.gov/cooling-water-intakes
| 4 | The checklist is to be used as an aid when taking a first in-depth look at a potential fish screening project to determine a) if the project is feasible and B) what major issues and participants need to be considered for implementation of the project. Unlike some of the other checklists, it is NOT a comprehensive design guide
About the Checklists:
The Education Committee of the BioEngineering Section (BES) of the American Fisheries Society (AFS) is providing a series of checklists for implementing fish passage and habitat projects as a service to our community of practice, especially newer practitioners and on the ground project managers. These checklists are provided with the intent of fostering more successful projects with fewer missteps and less backtracking. The following are a few notes to help make use of these checklists:
The checklists are targeted to common, small and moderate scale civil works projects being performed to remedy fish passage problems or for habitat improvement. They are not meant to address large and complex projects, nor will they perfectly serve all cases.
The checklists are to be used as prompts to consider what to enact or provide for a particular project type. The intent is not that each item should be performed, but the practitioner should consider each item to determine if it is required or beneficial to a successful project. It is unlikely that any project will enact ALL the items on a checklist, and conversely these checklists should be considered a starting point, with additional steps that may be necessary for a site or geographic area.
Individual checklists have been assembled for Aquatic Organism Passage, Fishways, Eel Passes, Dam Removals, Stream Profile Control, and Small Screens. Additional check lists may be included over time. Checklists were developed by experts in each type of project, based on the best available guidance rooted in existing science, engineering and training resources.
These checklists are not being endorsed by AFS or BES. There are other project checklists available from other authorities on these topics. Some can be found within training documents found at our other product, the Fish Passage Training Portal, available at the project homepage linked below. If you think the below collection of checklists would benefit from another category of project or have other feedback, please write to: water@terraserve.net
| Glossary: |  | A glossary of terms related to fish passage and stream restoration implementation has been compiled from various sources into a single file for ease of reference and can be downloaded from the project home page. | Project Home Page:
https://fishpassagejointcommittee.fisheries.org/resources/fishpassagetrainingportal/
| Fish Passage Training Portal: |  | A compendium of fish passage-related training resources and links to electronic data developed to provide a centralized and vetted list of resources to new practicitioners or those looking to expand their knowledge.

## Fish Screen Feasibility
Small fish screen Feasibility Checklist for Project Proponents |  |  |  |  | AFS-BES Education Ad Hoc 2023
adapted from Laura Wildman
See READ ME file before using, especially 316b designers
Subject |  |  | Question | Yes/No | Comments (from Project Proponents)
Ownership |  |  | Who owns the diversion? Are they willing/required to have it screened/rescreened? How much cost share are they willing to provide? |  |  | FALSE
Access and site fundamentals |  |  | Are there any insurmountable issues with getting permissions to access the diversion site? |  |  | TRUE
Is the diversion actively in use and unscreened/subs standardly screened for aquatic organism protection?
|  | Electric power | Is there electric service at site?
|  | Impoundment | Is there a dam or grade control associated with the diversion?
|  | High water | What is the highest water surface the diversion is normally operated at?
What is the 100 yr. flood water surface
|  | low water | What is the lowest water surface that the diversion is operated at? Is there (estimated) adequate bypass water at that time? What is the 95% exceedance flow (even if no diversion taking place at that time).
|  | other | Are there any conditions ( sedimentation, lack of bypass water/grade, storm debris, etc.) that makes on-stream screening prohibitive?
Current use (& economic value of diversion) | [5 empty] | TRUE
| Water supply |  | Use e.g. Irrigation, municipal, industrial (e.g. process water), timing/season and diversion rates ( average and peak) need to be determined
| Cooling water |  | Timing/season and diversion rates (average and peak) need to be determined. See READ ME note about 316b compliance
| Fire suppression |  | Is the diversion used for fire suppression?
| Hydroelectric |  | Is the diversion an active hydro-electric facility, or is a hydro-electric facility planned for the diversion in the near future? Will an off-channel bypass be needed? Will a tailwater exclusion be needed?
Water rights, and other legal rights |  |  | Do you know what legal water rights/limits are associated with this diversion? Are water user riparian or remote? Is there off-stream storage?
Sediment/topology
Has the diversion historically needed dredging? Is there adequate bypass water returning to stream
Infrastructure/utility impacts
| Retaining walls |  | Is there a retaining wall supporting the diversion or associated power supply (If so, comment on condition)?
| Subsurface utility pipes/lines1 |  | Are there any subsurface utility pipes or lines near the diversion?
| Overhead utilities |  | Are there any overhead wires that are low enough to create a problem for construction equipment during construction or operation/maintenance of a screen.
| Stream Gage |  | Is there a USGS or other stream gage near the diversion with a 10 year or greater record?
Geomorphic equilibrium2 |  |  | Is there any signs of geomorphic instabilities in the channel near the diversion? Estimate approximate slope of channel reach.
Historic/archeological3 |  |  | Are there any know historic or archeological concerns that could affect screening construction/maintenance ?
Sensitive species4 |  |  | Is there a Rare, Threatened or Endangered Species within the diversion area that could affect construction season?
Ecological Benefit |  |  | Fish Screen are usually placed to prevent entrainment of some or all life stages of targeted aquatic species. Target species and lifestage present at time of diversion use needs to be determined.
Cost & funding availability5 |  |  | Is there funding available to screen/rescreen the diversion?
Community concerns |  |  | Do you know of any community concerns that may hamper screening this diversion?
If the answers to the first and/or second questions are YES, then installation of a fish screen is not feasible.
If the answer to these two questions is NO than it is highly likely that installing a fish screen is feasible and likely would result in an overall improved ecological condition for the river system.
If one or more of the answers to the remaining questions was YES or UNKNOWN, then additional work is needed to ensure that installation of a fish screen is feasible, and can be completed with no increased human risks and minimum impacts to the environment and infrastructure/utilities.
DESCRIPTION & METHODS
1 |  | Subsurface Utilities | The municipality and or state should be contacted to help determine if there are subsurface utilities near the intake structure or within the upstream area of impact. It is especially critical to identify subsurface utilities that can be undermined or exposed by construction. However utilities paralleling the river or impoundment may also become an issue and should be identified. Most states have a services that can help identify these subsurface utilities (i.e. Ohio811; CT: Call Before You Dig; PA One Call)
2 |  | Geomorphic equilibrium | If the downstream channel is highly entrenched that could be a sign that a head cut is approaching from downstream. A headcut could lead to different rating curves for the site affecting both pumped and gravity diversions.
3 |  | Historic/archeological | Any structure over 50 years in age has the potential to be historic
4 |  | Sensitive or invasive species | Check the state databases to determine if there are any rare, threatened or endangered species upstream or downstream of the diversion.
5 |  | Cost & funding availability | There are numerous funding sources that can help reduce the cost of screening the diversion for owner or project proponents.